## Risk_Register
| Risk Register | 22.02.2022
|  | Before Mitigation |  |  |  | After mitigation |  |  | Owners / Actions
Risk Number | Name | Probability before mitigation (1,00=low; 3,00=high) | Severity before mitigation (1,00=low; 3,00=high) | Risk Score before mitigation | Mitigation | Probability after mitigation (1,00= low; 3,00=high) | Severity after mitigation (1,00= low; 3,00=high) | Risk Score after mitigation | Risk Owner (Member BoD / CommChair) | Action by | Action when (updated)
1 | Risk 1. In general, the risk of the AAE losing FMA sopport, attractiveness, trust, consensus, engagement and not open minded. | 1.5 | 3 | 4.5 | See the Risk Register Report (minutes BoD) | 1 | 3 | 3 | Gunn / Malcolm | See the Risk Register Report (minutes BoD) | Ongoing | Goal: reduce the probability from 1,50 to 1,00, and the goal for severity is the same after mitigation as before
2 | Risk 2. In general, risks related with Syllabus, CPD, Code of Conduct and MRA. | 2.5 | 3 | 7.5 | See the Risk Register Report (minutes BoD) | 2 | 3 | 6 | Luis / Christophe | See the Risk Register Report (minutes BoD) | Annual Meeting 2022 | Update: no change in the risk. Addition of one action plan: reintegration of the IFoA.
3 | Risk 3. In general, the risk of lossing attractiveness, competences and relevance as actuarial profession. | 1 | 3 | 3 | See the Risk Register Report (minutes BoD) | 1 | 2 | 2 | Inga / Henning | See the Risk Register Report (minutes BoD) | Annual Meeting 2022 | benchmark on risk peer level: due to significant impact from local association; potential failures in insurance market
4 | Risk 4. In general, the risk of lack of trust from external stakeholders. | 1 | 3 | 3 | See the Risk Register Report (minutes BoD) | 1 | 1.2 | 1.2 | Giampaolo / Tatiana | See the Risk Register Report (minutes BoD) | Ongoing | Update: no change in the risk.
5 | Risk 5. In general, the risk of lack of volunteers. | 2 | 3 | 6 | See the Risk Register Report (minutes BoD) | 2 | 2 | 4 | Philippe / Lauri | See the Risk Register Report (minutes BoD) | Ongoing
6 | Risk 6. In general, operational risks (Key persons, ciber risks, IT issues, litigation, compliance with competition legislation, GDPR). | 2 | 3 | 6 | See the Risk Register Report (minutes BoD) | 2 | 3 | 6 | Monique / Luis | See the Risk Register Report (minutes BoD) | End 2022 and Ongoing | Update: no change in the risk. Ongoing monitoring.

## Action plan risks 2&7
Authors | Luis and Christophe
Date | 22.02.2022 updated 30.06.2022
Risks 2. In general, risks related with Syllabus, CPD, Code of Conduct and MRA. | Action plan description | Action plan date/updated
Member Associations not complying with AAE Governance requirements (1.2) | Executing the informal review action plan by the General Assembly. | General Assembly 2022
Individual actuaries not acting / performing up to agreed standards resulting in questioning the integrity / quality of work of actuaries (2.3) | Raise awarness during President's meeting and webinars. | End of 2022
Lack of support of Syllabus, CPD and Code of Conduct. (3.5)
Education: Local universities do not fully cover new syllabus requirements; Risk: GAPs identified are not properly covered by other educational source. During Education Committee meeting in Sursee aprox 5 countries reported that will be able to cover syllabus; Other countries reported about GAPs identified. How to ensure that GAPs will be filled with appropriate source? Solution: AAE coordinated support? (5.1) | Compliance review is currently ongoing. | Spring meeting 2022
future of the fit and proper requirements of actuary/ risk manager (6.4) | Report to be drafted on AAE's strategy on Fit and Proper. | Spring meeting 2022
Reintegration of the IFoA in the MRA | Developping an updated MRA in collaboration with the IFoA. | 2026
Professionalisation of actuarial education/ specialization and impact on MRA (6.5) | Developping an updated MRA. | 2026
Underestimate the importance of the education which is the first concern, always important as you want to consolidate the traditional fields as if you want to develop the wider fields (9.3) | Compliance review is currently ongoing. | Spring meeting 2022
FMA not complying with AAE Governance requirements (Syllabus, CPD and Code of Conduct) and MRA. (19.4) | Compliance review is currently ongoing. Active collaboration with FMAs to ensure compliance. | General Assembly 2022
Future of the fit and proper requirements of actuary. (19.3) | Report to be drafter on AAE's strategy on Fit and Proper. | Spring meeting 2022

## Summary risk #3
| Sub-risks | AAE | Associations | Mitigation | Proposed mitigation plan | Update
1 | lossing attractiveness | Communication Panel (Extenal Stakeholders), AAE Priority list (wide fields- Board, Presidents etc) | Insights crucial to identify statuss (depends on size, local legislation requirements etc) | AAE next steps in line with requirements from member associations - Input collection | Development of Questioneer - Board support needed (to define representatives; Monique to find a time slot in Spring meeting)-expected to have questioneer prepared and provided to member associations before Summer; results analysed and identified specific action points for AAE till Autumn meetings. | Draft questionaire ready for Board review. Projected timeline: issue 2nd half of August with deadline to respond end October 2022
2 | competences | Sylabuss (design, assessment and updates), CPD, Webinars | Sylabuss Implementation | Sylabus: AAE support for implementation | support to cover some of GAPs identified during assessment (inital discussion will be discussed on AAE Education Spring meeting - to identify GAPs which could be covered with AAE support; next steps (online) discuss potential solutions proposed (including additional expenses etc); before summer brake discussion with AAE board; desicion in Autumn meeting/ Education/ Board
3 | relevance as actuarial profession | AAE Priority list (Role of actuary: Fit&Proper) | Insights crucial to identify statuss (depends on size, local legislation requirements etc) | AAE next steps in line with requirements from member associations - Input collection | in combination with the 1st row

## Action plan risk 4
Authors | Giampaolo and Tatiana
Date | 01.03.2022 updated 30.06.2022
Risks 4. In general, the risk of lack of trust from external stakeholders. | Action plan description | Action plan date | Action plan date
Losing credibility with major EU regulatory bodies (1.4); loss or degradation of trust towards the AAE by our main stakeholders, especially the EC and EIOPA (12.2); Loss of credibility with stakeholders e.g. AAE provides some input to EIOPA, or makes a public statement, which is demonstrably incorrect (15.1); Non relevance of AAE advice to European stakeholders. European stakeholders stop listening to AAE. (18.3) | Define the external stakeholders and organise tailor made communication | Ongoing | At the same time it is necessary to enlarge the data base of stakeholders and this topic is another matter CP is discussing.
European institutions losing trust in the integrity of the AAE as the representation of actuaries in Europe (2.4) | Recognise the appropriate language | Ongoing | substantially our approach is to strengthen the "visibility of substance" to increase relationships and the trust of stakeholders as we explained in the previous slides for the Board. We proposed the solution: a well designed and complete communication action plan. But this plan needs two important elements: high quality of the contents and a great ability to communicate to each stakeholder with appropriate way, approach and language. The attached scheme we prepared with CP we are already following is exactly the “photo” of this approach. So the action must continue in order to observe the reactions over time of the stakeholders, in qualitative and quantitative sense, as already indicated in the attached communication strategy.
Lack of trust from external stakeholders as a trusted advisor. (3.2) Loss of trust from institutions leading to AAE losing its status as a trusted advisor (10.2); Loss of trust AAE from institutions as a trusted advisor (16.4) |  | Ongoing
the risk for the AAE as an organisation. In this case I would see e.g. reputational risk (resulting from not being able to meet the expectation of members or stakeholders) (11.1);Reputational risk (Adverse publicity) (14.3); Reputational risk (Loss of trust AAE from institutions and Adverse publicity). (19.5) | Speak of "to strengthen our visibility of substance with stakeholders" | Ongoing
Actuarial profession no longer recognized as experts (SO2) (13.2) | Identify, support, use appropriate language/channel | Ongoing
Too many contradictory voices in Europe. Member associations doesn't recognize AAE as their voice towards EU and speaks for themselves with a huge variety of opinions. (18.4) | Use CP scheme | Ongoing

## Action plan risk #5
Authors | Philippe and Lauri
Risk 5. In general, the risk of lack of volunteers.
Date | 23.02.2022

## Action plan risk 6
Authors | Luis and Monique
Date | 23.02.2022
Risks 6. In general, operational risks (Key persons, ciber risks, IT issues, litigation, compliance with competition legislation, GDPR…) | Action plan description | Action plan date | Update - till end 2022
Key person risk in Secretariat (3.3) and secretariat key person risk & Maikel (6.1) and Operational risk (key person) (14.1) and Operational risk: Key persons. (19.2) | Monitor activities (increased) vs available capacity. Act in case of unbalance/unavailability. | ongoing | Recruitment process to start for successor of Maikel, expected to be finalised (well) before year end.
Business Continuity for AAE Office (13.3) | Monitor activities (increased) vs available capacity. Act in case of unbalance/unavailability. | ongoing | Recruitment of successor will most likely include more working hours for successor.
Cyber risk (3.4) | Continue to monitor via our IT suppliers for IT and website | ongoing | ongoing
MRA litigation risk and/or loss of credibility if some MAs are found to be deliberately not following its spirit, should also in my opinion be given priority. (10.4) | Not sure what is exactly meant here in relation to operations of the secretariat
breach of compliance, especially with respect to the competition legislation (12.3) | Not sure what is exactly meant here in relation to operations of the secretariat. Shouldn't this be part of the Compliance review of Christophe?
GDPR (14.5) | Advice gained from GT experts and implemented. Continue to update the database and remove details if necessary. | ongoing | ongoing
Operational difficulties arising due to volunteer members/small staff due to e.g. IT issues, personality clashes etc. (15.5) | Volunteer issues: prepare earlier to allow volunteers more time. Also reviewers are volunteers. IT issues are closely monitored and are usually fixed within hours. | ongoing | ongoing
Risk of not managing the work in AAE internally (AAE secretary, meetings, discussions etc.) (17.5) | Monitor activities (increased) vs available capacity. Act in case of unbalance/unavailability. | ongoing | Recruitment of successor will most likely include more working hours for successor.

## Grouping_into_9_categories
| Risk Register | 2022-02-22
Grouping into 9 categories all the risks from the Stakeholder's feedback (19 people have pointed out 5 risks, total of 95 risks).
1 | Risks 1. In general, the risk of the AAE losing FMA sopport, attractiveness, trust, consensus, engagement and not open minded. | Member Associations leaving the MRA (1.1). | Other associations entering into bilateral agreements with FMAs and making AAE's position weaker (1.3) | National associations supporting the goal and the work of AAE (2.5) | Lack of MA support- (3.1) | Loss of support of MAs (4.1) | engagement of big associations (6.2) | Potential conflict of interest between member associations : the heterogeneous composition of the membership (size, development, political position, …) implies different objectives. Decision making is dominated by the strongest and most powerful associations, less strong association can lose interest. (8.1) | Forget to involve more and more small countries in Europe that have problems to be attending due to costs, sizes and resources. Hybrid meetings can be an help but it is necessary to have a wider plan. I think that European Actuaries must increase and develop together with a unique development's project. The risk is to proceed each on his own without a common strategy and goal [absolutely to be avoided] (9.5) | Overthinking about governance, first because AAE is an Association and not a private firm or similar, second because it must not distract us from ours important goals and mission, for instance lobbies, the development of actuarial profession everywhere, the education, etc.... (9.4) | Loss of consensus regarding AAE strategic objectives (10.1) | Be closed and not open, and above all attention to become self-referential. Until 2010 in Italy actuaries were a close world; through a new strategy based on many projects, particulalrly communication, all changed.Afterwards the self-referential risk starts. It is a very long story if You wish I can explain briefly better during the next Board Meeting (9.1) | Lack of MA support (10.3) | the risk for the AAE as an organisation:lack of support by member organisations (11.2) | loss of one of the biggest members and/or degradation in the appreciation towards the AAE by members of our member associations – i.e. loss of actuaries volunteering to work for the AAE (12.1) | Reputation AAE as institutional organization (SO1/SO3)- see further details TAB Wilhelm (13.1) | Strategic risk : lack of support from MAs (14.2) | Loss of credibility with members e.g. AAE makes some statements (or perhaps doesn’t make a statement) which does not reflect the majority views of the members, or is inaccurate/unprofessional (15.2) | Loss of member associations on grounds of lack of added value, or cost (15.3) | Loss of an MA for “political” reasons e.g. UK, Poland (15.4) | Lack of MA support (16.1) | Loss of consensus of AAE strategic objectives (16.3) | Risk of losing support from member associations to the AAE work. From insurance committees perspective especially those who are involved in the various working groups (17.1) | Risk of using time / resources (volunteers) on topics that are not interesting for member asosciations. This risk is also about not being able to communicate the results clearly enough. (17.2) | Risk of not being able to identify the AAE overall priorities in a way that helps steering the ground level work (working groups) and vise versa, doing ground work that is not used in AAE in the end. (17.3) | AAE forgets its corporate mission and focus on communication or pure CPD or something else. (18.2) | Too many contradictory voices in Europe. Member associations doesn't recognize AAE as their voice towards EU and speaks for themselves with a huge variety of opinions. (18.4) | Member associations leave AAE. They may create a competitor to AAE or simply work alone in Europe. (18.5) | Strategic risk : lack of support from FMAs (19.1)
2 | Risks 2. In general, risks related with Syllabus, CPD, Code of Conduct and MRA. | Member Associations not complying with AAE Governance requirements (1.2) | Individual actuaries not acting / performing up to agreed standards resulting in questioning the integrity / quality of work of actuaries (2.3) | Lack of support of Syllabus, CPD and Code of Conduct. (3.5) | Education: Local universities do not fully cover new syllabus requirements; Risk: GAPs identified are not properly covered by other educational source. During Education Committee meeting in Sursee aprox 5 countries reported that will be able to cover syllabus; Other countries reported about GAPs identified. How to ensure that GAPs will be filled with appropriate source? Solution: AAE coordinated support? (5.1) | future of the fit and proper requirements of actuary/ risk manager (6.4) | profilization of actuarial education/ specialization and impact on MRA (6.5) | underestimate the importance of the education which is the first concern, always important as you want to consolidate the traditional fields as if you want to develop the wider fields (9.3) | FMA not complying with AAE Governance requirements (Syllabus, CPD and Code of Conduct) and MRA. (19.4) | Future of the fit and proper requirements of actuary. (19.3)
3 | Risks 3. In general, the risk of lossing attractiveness, competences and relevance as actuarial profession. | The profession losing its attractiveness to students / young professionals (2.1) | don't search to enlarge our professional and business horizon towards other kind of clients and fields (any kind of firms - ERM - or financial world, for instance). It is a significant risk particularly if you want to develop the wider fields (9.2) | Loss of relevance of profession (e.g. due to non-integration of data scientist, redundancy with insurance industry position) (4.2) | Loss of relevance of AAE in future due to not appropriately including younger actuaries in responsible positions (4.3) | Actuarial services becoming a commodity : some users of services and external stakeholders are looking at actuaries as number crunchers with no added value. Modern technology and general view on the role of the actuary can reduce the role of actuaries to secondary aspects such as reporting, number crunching … The decrease in value of the profession leads to the decrease of relevance of the associations and the AAE. (8.3) | Actuaries are attracted by other fields such as risk management and data science and take distance to find more support in other organisations. (8.4) | failure in establishing relevance of actuaries in so-called (prioritised) wider fields, e.g., risk management and data science (12.4) | New competition - Some other organisation (e.g. IAA or new actuarial grouping) succeeds in persuading actuaries / MAs to switch allegiance from AAE / Data science (16.2)
4 | Risks 4. In general, the risk of lack of trust from external stakeholders. | Losing credibility with major EU regulatory bodies (1.4) | European institutions losing trust in the integrity of the AAE as the representation of actuaries in Europe (2.4) | Lack of trust from external stakeholders as a trusted advisor. (3.2) | Loss of trust of European Institutions in AAE, esp. due to lack of independent positions (4.4) | The appreciation of stakeholders (European institutions, other professional organisations) is reduced because of lack of professionalism, recognition is disappearing because of lack of structure. (8.5) | Loss of trust from institutions leading to AAE losing its status as a trusted advisor (10.2) | the risk for the AAE as an organisation. In this case I would see e.g. reputational risk (resulting from not being able to meet the expectation of members or stakeholders) (11.1) | loss or degradation of trust towards the AAE by our main stakeholders, especially the EC and EIOPA (12.2) | Actuarial profession no longer recognized as experts (SO2) (13.2) | Reputational risk (Adverse publicity) (14.3) | Loss of credibility with stakeholders e.g. AAE provides some input to EIOPA, or makes a public statement, which is demonstrably incorrect (15.1) | Loss of trust AAE from institutions as a trusted advisor (16.4) | Non relevance of AAE advice to European stakeholders. European stakeholders stop listening to AAE. (18.3) | Too many contradictory voices in Europe. Member associations doesn't recognize AAE as their voice towards EU and speaks for themselves with a huge variety of opinions. (18.4) | Reputational risk (Loss of trust AAE from institutions and Adverse publicity). (19.5)
5 | Risks 5. In general, the risk of lack of volunteers. | Not having new generations contributing to the AAE and lack of volunteers (1.5) | Committees’ work: lack of volunteers. Risk: deliverables on consultation papers, view summary on specific topic etc are not on sufficient quality. Example, Pensions committee – a lot of discussion points on international/ European level however AAE Pension committee has very limited number of volunteers. Solution: AAE provided support – paid expert (eg. Insurance Committee)? (5.2) | loss of one of the biggest members and/or degradation in the appreciation towards the AAE by members of our member associations – i.e. loss of actuaries volunteering to work for the AAE (12.1) | Risk of not finding experts, volunteers, expertize, to further topics that are identified as high priority in AAE. E.g. digitalization is key area with rare expertize. (17.4) | Risk of lack of production. Committes meet but produce nothing or nothing Discussions. Travels. But no outputs. Reduction of the number of voluntaries. (18.1)
6 | Risks 6. In general, operational risks (Key persons, ciber risks, IT issues, litigation, compliance with competition legislation, GDPR…) | Key person risk in Secretariat (3.3) | Cyber risk (3.4) | secretariat key person risk & Maikel (6.1) | MRA litigation risk and/or loss of credibility if some MAs are found to be deliberately not following its spirit, should also in my opinion be given priority. (10.4) | breach of compliance, especially with respect to the competition legislation (12.3) | Business Continuity for AAE Office (13.3) | Operational risk (key person) (14.1) | Cyber Risk (14.4) | GDPR (14.5) | Operational difficulties arising due to volunteer members/small staff due to e.g. IT issues, personality clashes etc. (15.5) | Key person risk (16.5) | Risk of not managing the work in AAE internally (AAE secretary, meetings, discussions etc.) (17.5) | Operational risk: Key persons. (19.2)
7 | Risks 7. In general, risks related with the role of actuaries topic. | Role of actuary: on-going inputs/ work required. Risk: important topic but work stoped due to closed WG. Solution: AAE defines what are major goal for topic Role of actuary and establish new WG/TF? (5.3) | Role of Actuaries in SS and Pensions (7.3) | Other professions taking over actuarial tasks [regarding that there is no level playing field in Europe on (legal) recognition]. (2.2)
8 | Risks 8. In general, risks related with sustainability, consumer protection, economical and environmental crisis. | Address sustainability topic (6.3) | Adequacy and sustainability of pensions (7.1) | Customer protection and Intergenerational Fairness (7.2) | Positioning of the AAE as part of the problem, and not as part of the solution, in the area of turning the world sustainable. (12.5) | Economical and environmental Crisis (Climate, interest rates) weakens EU and as consequence AAE (13.4) | Risk from actuarial perspective: i. Solvency II: Non-appropriate amendments to SII framework (LTG-measures, valuation principles) ii. Strengthening the role of insurers as investors vs. policyholder protection (“same risk – same capital” endangered?) iii. Inadequate disclosure requirements SII and sustainability iv. Interaction micro- and macroprudential supervision ( higher workload for undertakings?) v. Recovery and Resolution: Separate Resolution Authorities (to be set up) vs. National Competent Authorities (Interaction unclear). (11.3)
9 | Risks 9. In general, risks related with conflict of interests. | Potential conflict of interest between role in AAE and interest of local association : colleagues in responsible positions of AAE are supposed to defend the strategy and objectives of the AAE which are not necessarily aligned with the objectives of the home association. (8.2)

## Risks_Feedback_Stakeholder
| Risk Register | 2021-11-10
Top 5 risks. Feedback from Board, CommChairs and Advisory Panel
| Name | Risk 1 | Risk 2 | Risk 3 | Risk 4 | Risk 5
1 | Christophe Heck | Member Associations leaving the MRA (1.1). | Member Associations not complying with AAE Governance requirements (1.2) | Other associations entering into bilateral agreements with FMAs and making AAE's position weaker (1.3) | Losing credibility with major EU regulatory bodies (1.4) | Not having new generations contributing to the AAE and lack of volunteers (1.5)
2 | Henning Wergen | The profession losing its attractiveness to students / young professionals (2.1) | Other professions taking over actuarial tasks [regarding that there is no level playing field in Europe on (legal) recognition]. (2.2) | Individual actuaries not acting / performing up to agreed standards resulting in questioning the integrity / quality of work of actuaries (2.3) | European institutions losing trust in the integrity of the AAE as the representation of actuaries in Europe (2.4) | National associations supporting the goal and the work of AAE (2.5)
3 | Gunn Albertsen | Lack of MA support- (3.1) | Lack of trust from external stakeholders as a trusted advisor. (3.2) | Key person risk in Secretariat (3.3) | Cyber risk (3.4) | Lack of support of Syllabus, CPD and Code of Conduct. (3.5)
4 | Lutz Wilhelmy | Loss of support of MAs (4.1) | Loss of relevance of profession (e.g. due to non-integration of data scientist, redundancy with insurance industry position) (4.2) | Loss of relevance of AAE in future due to not appropriately including younger actuaries in responsible positions (4.3) | Loss of trust of European Institutions in AAE, esp. due to lack of independent positions (4.4)
5 | Inga Helmane | Education: Local universities do not fully cover new syllabus requirements; Risk: GAPs identified are not properly covered by other educational source. During Education Committee meeting in Sursee aprox 5 countries reported that will be able to cover syllabus; Other countries reported about GAPs identified. How to ensure that GAPs will be filled with appropriate source? Solution: AAE coordinated support? (5.1) | Committees’ work: lack of volunteers. Risk: deliverables on consultation papers, view summary on specific topic etc are not on sufficient quality. Example, Pensions committee – a lot of discussion points on international/ European level however AAE Pension committee has very limited number of volunteers. Solution: AAE provided support – paid expert (eg. Insurance Committee)? (5.2) | Role of actuary: on-going inputs/ work required. Risk: important topic but work stoped due to closed WG. Solution: AAE defines what are major goal for topic Role of actuary and establish new WG/TF? (5.3)
6 | Mária Kamenárová | secretariat key person risk & Maikel (6.1) | engagement of big associations (6.2) | address sustainability topic (6.3) | future of the fit and proper requirements of actuary/ risk manager (6.4) | profilization of actuarial education/ specialization and impact on MRA (6.5)
7 | Tatiana Bitunska | Adequacy and sustainability of pensions (7.1) | Customer protection and Intergenerational Fairness (7.2) | Role of Actuaries in SS and Pensions (7.3)
8 | Karel Goossens | Potential conflict of interest between member associations : the heterogeneous composition of the membership (size, development, political position, …) implies different objectives. Decision making is dominated by the strongest and most powerful associations, less strong association can lose interest. (8.1) | Potential conflict of interest between role in AAE and interest of local association : colleagues in responsible positions of AAE are supposed to defend the strategy and objectives of the AAE which are not necessarily aligned with the objectives of the home association. (8.2) | Actuarial services becoming a commodity : some users of services and external stakeholders are looking at actuaries as number crunchers with no added value. Modern technology and general view on the role of the actuary can reduce the role of actuaries to secondary aspects such as reporting, number crunching … The decrease in value of the profession leads to the decrease of relevance of the associations and the AAE. (8.3) | Actuaries are attracted by other fields such as risk management and data science and take distance to find more support in other organisations. (8.4) | The appreciation of stakeholders (European institutions, other professional organisations) is reduced because of lack of professionalism, recognition is disappearing because of lack of structure. (8.5)
9 | Giampaolo Crenca | Be closed and not open, and above all attention to become self-referential. Until 2010 in Italy actuaries were a close world; through a new strategy based on many projects, particulalrly communication, all changed.Afterwards the self-referential risk starts. It is a very long story if You wish I can explain briefly better during the next Board Meeting (9.1) | don't search to enlarge our professional and business horizon towards other kind of clients and fields (any kind of firms - ERM - or financial world, for instance). It is a significant risk particularly if you want to develop the wider fields (9.2) | underestimate the importance of the education which is the first concern, always important as you want to consolidate the traditional fields as if you want to develop the wider fields (9.3) | overthinking about governance, first because AAE is an Association and not a private firm or similar, second because it must not distract us from ours important goals and mission, for instance lobbies, the development of actuarial profession everywhere, the education, etc.... (9.4) | forget to involve more and more small countries in Europe that have problems to be attending due to costs, sizes and resources. Hybrid meetings can be an help but it is necessary to have a wider plan. I think that European Actuaries must increase and develop together with a unique development's project. The risk is to proceed each on his own without a common strategy and goal [absolutely to be avoided] (9.5)
10 | Malcolm Kemp | Loss of consensus regarding AAE strategic objectives (10.1) | Loss of trust from institutions leading to AAE losing its status as a trusted advisor (10.2) | Lack of MA support (10.3) | MRA litigation risk and/or loss of credibility if some MAs are found to be deliberately not following its spirit, should also in my opinion be given priority. (10.4)
11 | Siegbert Baldauf | the risk for the AAE as an organisation. In this case I would see e.g. reputational risk (resulting from not being able to meet the expectation of members or stakeholders) (11.1) | the risk for the AAE as an organisation:lack of support by member organisations (11.2) | Risk from actuarial perspective: i. Solvency II: Non-appropriate amendments to SII framework (LTG-measures, valuation principles) ii. Strengthening the role of insurers as investors vs. policyholder protection (“same risk – same capital” endangered?) iii. Inadequate disclosure requirements SII and sustainability iv. Interaction micro- and macroprudential supervision ( higher workload for undertakings?) v. Recovery and Resolution: Separate Resolution Authorities (to be set up) vs. National Competent Authorities (Interaction unclear). (11.3)
12 | Esko Kivisaari | loss of one of the biggest members and/or degradation in the appreciation towards the AAE by members of our member associations – i.e. loss of actuaries volunteering to work for the AAE (12.1) | loss or degradation of trust towards the AAE by our main stakeholders, especially the EC and EIOPA (12.2) | breach of compliance, especially with respect to the competition legislation (12.3) | failure in establishing relevance of actuaries in so-called (prioritised) wider fields, e.g., risk management and data science (12.4) | positioning of the AAE as part of the problem, and not as part of the solution, in the area of turning the world sustainable. (12.5)
13 | Wilhelm Schneemeier | Reputation AAE as institutional organization (SO1/SO3)- see further details TAB Wilhelm (13.1) | Actuarial profession no longer recognized as experts (SO2) (13.2) | Business Continuity for AAE Office (13.3) | Economical and environmental Crisis (Climate, interest rates) weakens EU and as consequence AAE (13.4)
14 | Matthias Pillaudin | Operational risk (key person) (14.1) | Strategic risk : lack of support from MAs (14.2) | Reputational risk (Adverse publicity) (14.3) | Cyber Risk (14.4) | GDPR (14.5)
15 | Philip Shier | Loss of credibility with stakeholders e.g. AAE provides some input to EIOPA, or makes a public statement, which is demonstrably incorrect (15.1) | Loss of credibility with members e.g. AAE makes some statements (or perhaps doesn’t make a statement) which does not reflect the majority views of the members, or is inaccurate/unprofessional (15.2) | Loss of member associations on grounds of lack of added value, or cost (15.3) | Loss of an MA for “political” reasons e.g. UK, Poland (15.4) | Operational difficulties arising due to volunteer members/small staff due to e.g. IT issues, personality clashes etc. (15.5)
16 | Philippe Demol | Lack of MA support (16.1) | New competition - Some other organisation (e.g. IAA or new actuarial grouping) succeeds in persuading actuaries / MAs to switch allegiance from AAE / Data science (16.2) | Loss of consensus of AAE strategic objectives (16.3) | Loss of trust AAE from institutions as a trusted advisor (16.4) | Key person risk (16.5)
17 | Lauri Saraste | Risk of losing support from member associations to the AAE work. From insurance committees perspective especially those who are involved in the various working groups (17.1) | Risk of using time / resources (volunteers) on topics that are not interesting for member asosciations. This risk is also about not being able to communicate the results clearly enough. (17.2) | Risk of not being able to identify the AAE overall priorities in a way that helps steering the ground level work (working groups) and vise versa, doing ground work that is not used in AAE in the end. (17.3) | Risk of not finding experts, volunteers, expertize, to further topics that are identified as high priority in AAE. E.g. digitalization is key area with rare expertize. (17.4) | Risk of not managing the work in AAE internally (AAE secretary, meetings, discussions etc.) (17.5)
18 | Thomas Béhar | Risk of lack of production. Committes meet but produce nothing or nothing Discussions. Travels. But no outputs. Reduction of the number of voluntaries. (18.1) | AAE forgets its corporate mission and focus on communication or pure CPD or something else. (18.2) | Non relevance of AAE advice to European stakeholders. European stakeholders stop listening to AAE. (18.3) | Too many contradictory voices in Europe. Member associations doesn't recognize AAE as their voice towards EU and speaks for themselves with a huge variety of opinions. (18.4) | Member associations leave AAE. They may create a competitor to AAE or simply work alone in Europe. (18.5)
19 | Luis Saez de Jauregui | Strategic risk : lack of support from FMAs (19.1) | Operational risk: Key persons. (19.2) | Future of the fit and proper requirements of actuary. (19.3) | FMA not complying with AAE Governance requirements (Syllabus, CPD and Code of Conduct) and MRA. (19.4) | Reputational risk (Loss of trust AAE from institutions and Adverse publicity). (19.5)