## Slide 1
AAE Strategic Plan Priorities and tasks identified in 2024
19 November 2024

## Slide 2
Pillar | Project / Task | Expected delivery | Responsibility (November 2024)
Setting Guidance and Standards (4) | MRA (ongoing; started before October 2023) | 31 December 2024 | 
Setting Guidance and Standards (4) | Review of Code of Professional Conduct | GA 2025 | 
AAE Operations & Governance (5) | Review of AAE Statutes | GA 2025 | 
Setting Guidance and Standards (4) | CPD Compliance Review | 31 December 2024 | 
Development of the Profession (1) | Play a prominent role in relevant European Consultations | Consultations/ December 2024 | 
Development of the Profession (1) | Wider Fields: Artificial Intelligence | On-going | 
Development of the Profession (1) | Wider Fields: Sustainability (ESG) | Ongoing | 
AAE Operations & Governance (5) | AAE Own Sustainability Project | Phase 1: Approval/ December 2024 Phase 2: On-going | 
Status/ November 2024 (1 from 2)
ProfC/ Statutes TF
EduC
Insurance/ SII WG
RMC/ SCrR WG
Secretariat
Pensions Com.
RMC
Stephanos
ProfC/ CDC TF
Insurance Com.
Board
Committee Chairs
Comm. Panel
Siegbert
ProfC
ProfC/ AI-DS WG
Pensions Com./ IORPII TF
Stephanos
ProfC/ AI-DS WG
RMC/ SCrR WG
Stephanos
Relevant Committees & WGs
Stephanos
EduC/ CPD AI WG
EduC/ CPD AI WG
RMC
For discussion
ProfC
Stephanos
RMC/ SCrR WG
Siegbert

## Slide 3
Pillar | Project / Task | Expected delivery | Responsibility (November 2024)
Development of the Profession (1) | Core Areas: Insurance | Ongoing/ limited resources due to SII consultations | 
Development of the Profession (1) | Core Areas: Pensions | Ongoing / IORP II Position paper | 
Communication and Stakeholder Relationship Management (2) | On-going implementation of communication process: "drumbeat" and "ad hoc" comms. | Ongoing | 
Communication and Stakeholder Relationship Management (2) | Implementation of Stakeholder Management Framework | ??? | 
Communication and Stakeholder Relationship Management (2) | Competency framework to support education and CPD | GA 2025 | 
AAE Operations & Governance (5) | Establish Publication Process / Policy | Before summer 2025 | 
AAE Operations & Governance (5) | Review Target Operating Model | Interim April 2025/ GA 2025 | 
Status/ November 2024 (2 from 2)
EduC
Insurance/ SII WG
RMC/ SCrR WG
Secretariat
Pensions Com.
RMC
Stephanos
Insurance Com.
Board
Committee Chairs
Comm. Panel
Siegbert
ProfC
ProfC/ AI-DS WG
Pensions Com./ IORPII TF
Relevant Committees & WGs
Stephanos
EduC/ CPD AI WG
For discussion
Specific Task Force
Stephanos
Stephanos
Insurance/ SII WG
Siegbert
Insurance Com.
Pensions Com.
Pensions Com./ IORPII TF
Comm. Panel
Comm. Panel
EduC
Relevant Committees & WGs

## Slide 4: Known information discussed/ agreed in 2024 (only for reference purposes)

## Slide 5
AAE Strategic Objectives and Key Pillars
Development of the Actuarial Profession in traditional areas and wider fields
Communication and Stakeholder Relationship Management
Lifelong Learning and Exchange of Ideas
Setting Guidance and Standards
for the Actuarial Profession
AAE Operations and Governance
1
2
3
4
5
Key Pillars
Enhance Relations with European Institutions
Promote Professionalism
Promote a European Community of Actuaries
1
2
3
Strategic Objectives Vision statement
  The vision of the AAE is for actuaries throughout Europe to be recognised as the leading quantitative professional advisers in financial services, risk management and social protection, contributing to the well‐being of society, and for European institutions to recognise the valuable role that the AAE plays as a leading source of advice on actuarial and related issues.

## Slide 6
Mapping of SO 1-3 to Pillars 1-5
Strategic Objectives | 
Enhance Relations with European Institutions | Establish and maintain relationships with key European institutions, so that the AAE can effectively provide them with high quality professional advice to improve the soundness of decisions from an actuarial perspective. Play a prominent role in shaping the development of new European legislation, and in the review and refinement of existing legislation, affecting the work of actuaries in traditional areas and in wider fields as actuaries extend their areas of involvement; Reinforce existing relationships with the European Commission and EIOPA; Build and enhance relationships with the European Parliament and the Council of the EU; and Maintain contact with other European organisations such as industry and consumer protection bodies.
Promote Professionalism | Promote consistent standards of education and professionalism among actuaries in Europe. prescribe minimum requirements for the education of actuaries to be applied by member associations; facilitate continuing professional development of actuaries; ensure that all member associations have a code of professional conduct which reflects at least the requirements of the AAE’s Code of Professional Conduct, and an appropriate disciplinary process; develop and maintain model standards of actuarial practice for work undertaken by actuaries in relation to EU regulatory requirements; maintain a mutual recognition agreement which is consistent with the requirements of the EU Recognition of Professional Qualifications Directive; support the development and recognition of individual member associations; help to ensure that regulated actuarial work is performed by those properly qualified to undertake it and subject to relevant professional and technical actuarial standards; and support the development and recognition of actuarial work in wider fields as actuaries extend their areas of involvement.
Promote a European Community of Actuaries | Promote a European community of actuaries between AAE member associations, their members and the AAE. encourage the exchange of information and ideas; facilitate networking between actuaries, especially in wider fields; strengthen awareness among member associations and their members of the work of the AAE; and facilitate mutual assistance between member associations.
1
2
3
2
2
2
1
3
4
4
4
4
4
4
2
5
3
3
1
3
4
3
1
3
3
5

## Slide 7
Key Pillars | Pillar Definition | Link with SO | Long-List of defined Priorities
Pillar 1 | Development of the Actuarial Profession in traditional areas and wider fields | Play a prominent role in shaping the development of new European legislation, and in the review and refinement of existing legislation, affecting the work of actuaries in traditional areas and in wider fields as actuaries extend their areas of involvement; ___ Support the development and recognition of individual member associations; Support the development and recognition of actuarial work in wider fields as actuaries extend their areas of involvement | Concentrate on selected wider fields: AI & Sustainability Maintain Core areas: Insurance and Pensions, including Solvency II and IORP II reviews, Consumer Protection Establish process for identifying wider fields with value added for the Actuarial Profession (Board/ Committee cooperation: postponed due to limited resources)
Pillar 2 | Communication and Stakeholder Relationship Management | Reinforce existing relationships with the European Commission and EIOPA; Build and enhance relationships with the European Parliament and the Council of the EU; Strengthen awareness among member associations and their members of the work of the AAE ___ Maintain contact with other European organisations such as industry and consumer protection bodies | Strengthening of Stakeholder Management and Monitoring Organising of Webinars, Congresses and other events (On-going / recurring) On-going implementation of communication process: "drumbeat" and "ad hoc" communications
Long-List of Priorities (1 from 3)

## Slide 8
Key Pillars | Pillar Definition | Link with SO | Long-List of defined Priorities
Pillar 3 | Lifelong Learning and Exchange of Ideas | Prescribe minimum requirements for the education of actuaries to be applied by member associations; Encourage the exchange of information and ideas; Facilitate networking between actuaries, especially in wider fields; Facilitate mutual assistance between member associations ____ Facilitate continuing professional development of actuaries; Support the development and recognition of individual member associations; Support the development and recognition of actuarial work in wider fields as actuaries extend their areas of involvement | Competency framework to support education and CPD Attractiveness of the profession (on-going not a project)
Pillar 4 | Setting Guidance and Standards for the Actuarial Profession | Ensure that all member associations have a code of professional conduct which reflects at least the requirements of the AAE’s Code of Professional Conduct, and an appropriate disciplinary process; Develop and maintain model standards of actuarial practice for work undertaken by actuaries in relation to EU regulatory requirements; Help to ensure that regulated actuarial work is performed by those properly qualified to undertake it and subject to relevant professional and technical actuarial standards; ____ Maintain a mutual recognition agreement which is consistent with the requirements of the EU Recognition of Professional Qualifications Directive Support the development and recognition of individual member associations; Support the development and recognition of actuarial work in wider fields as actuaries extend their areas of involvement | Review of Code of Professional Conduct (to be initiated) CPD Compliance Review (started in 2024/ Vilnius) Review of ESAPs and EANs (as necessary) Engagement with volunteers (Ongoing) European Actuarial Brand (Limited buy-in/ Postponed)
Long-List of Priorities (2 from 3)

## Slide 9
Key Pillars | Pillar Definition | Link with SO | Long-List of defined Priorities
Pillar 5 | AAE Operations and Governance | ____ Maintain contact with other European organisations such as industry and consumer protection bodies; Maintain a mutual recognition agreement which is consistent with the requirements of the EU Recognition of Professional Qualifications Directive | MRA (ongoing; started before October 2023); Review Target Operating Model and assessing the need for additional staff resources; Review of AAE Statutes (to be initiated); Establish Publication Process / Policy; AAE Own Sustainability Monitoring of economic resources (Ongoing/ Budget Forecast)
Long-List of Priorities (3 from 3)

## Slide 10: Implementation of Strategic plan
Communicate
the Plan
1
Assign roles and responsibilities
2
Mobilize
resources
3
Execute
the Plan
4
Monitor and evaluate the Plan
5
Clear, consistent, and continuous throughout the implementation process.
Communication about revised Strategy is successfully started:
ECA 2024;
TEA 09 2024
Planned:
GA 2024
On-going
Clearly defined, documented, and communicated to everyone involved
Allocated and managed efficiently and effectively, according to the priorities and timelines.
According to the action plans that have been developed.
Measuring and reporting the progress and performance on regular basis.
Discussed during the Board meeting (September 11, 2024)
Proposal disclosed on the next slides

## Slide 11
Structure of roles
AAE Board | Strategy (SO 1 – 3) |  |  |  | 
AAE Board with involvement of AAE Committees | Pillar 1 Development of the Actuarial Profession in traditional areas and wider fields | Pillar 2 Communication and Stakeholder Relationship Management | Pillar 3 Lifelong Learning and Exchange of Ideas | Pillar 4 Setting Guidance and Standards for the Actuarial Profession | Pillar 5 AAE Operations and Governance
AAE Board with involvement of AAE Committees | List of priorities identified (link with SO) |  |  |  | 
AAE Committees, AAE Secretariat/ project managers | Detailed work on allocated priorities/ execution (Scope, Deliverable, Resources: existing or new TF/ WG) Board members volunteered to provide support (if required/ depends on priority) |  |  |  | 
AAE Panels involvement | Expected that AAE Panel’s involvement (Advisory/Nominations/Communication) assessed by assigned AAE Committee (in line with ToR of AAE Panel’s) |  |  |  | 
Reporting to AAE Board | Link to topics reported by the Committees; expected regularity at least on quarterly basis (depends on priority; monthly basis) |  |  |  | 
Depending on Resource availability | Work on additional initiatives by AAE Commiittees (not identified as priorities in the Strategic Plan) |  |  |  | 
Refer to assigned responsibilities (Slide 12)
Refer to Board support (Slide 13)

## Slide 12
# | Pillar | Project / Task | Responsibility
 | Setting Guidance and Standards (4) | MRA (ongoing; started before October 2023) | 
 | Setting Guidance and Standards (4) | Review of Code of Professional Conduct (to be initiated) | 
 | Setting Guidance and Standards (4) | CPD Compliance Review (started in 2024/ Vilnius) | 
 | Development of the Profession (1) | Play a prominent role in relevant European Consultations | 
 | Development of the Profession (1) | Wider Fields: Artificial Intelligence | 
 | Development of the Profession (1) | Wider Fields: Sustainability (ESG) | 
 | Development of the Profession (1) | Core Areas: Insurance | 
 | Development of the Profession (1) | Core Areas: Pensions | 
 | Communication and Stakeholder Relationship Management (2) | On-going implementation of communication process: "drumbeat" and "ad hoc" comms. | 
 | Communication and Stakeholder Relationship Management (2) | Implementation of Stakeholder Management Framework | 
 | Communication and Stakeholder Relationship Management (2) | Competency framework to support education and CPD | 
 | AAE Operations & Governance (5) | Review of AAE Statutes (to be initiated) | 
 | AAE Operations & Governance (5) | Establish Publication Process / Policy | 
 | AAE Operations & Governance (5) | Review Target Operating Model | 
 | AAE Operations & Governance (5) | AAE Own Sustainability Project | 
Assigning Responsibilities
ProfC
EduC
Insurance/ SII WG
RMC/ SCrR WG
Secretariat
Pensions Com.
RMC
Stephanos
ProfC
ProfC
Insurance Com.
Board
Committee Chairs
Comm. Panel
Siegbert
ProfC
ProfC/ AI-DS WG
Pensions Com./ IORPII TF
Siegbert
Stephanos
ProfC/ AI-DS WG
RMC/ SCrR WG
Insurance/ SII WG
Pensions Com./ IORPII TF
Comm. Panel
Comm. Panel
EduC
Board
Stephanos
Board
Stephanos
Stephanos
Secretariat
Secretariat
Stephanos
Stephanos
Stephanos
Specific Task Force
RMC/ SCrR WG
ProfC
Stephanos
Specific Task Force
Relevant Committees & WGs
Stephanos
Prepared in July 2024
EduC/ CPD AI WG
EduC/ CPD AI WG

## Slide 13
AAE Key Pillars: Board support
Key Pillars | New definition under “Pillar” approach | Board support
Pillar 1 | Development of the Actuarial Profession in traditional areas and wider fields | Malcolm, Lutz, Jette, Inga
Pillar 2 | Communication and Stakeholder Relationship Management | Frank, Jette, Lourdes
Pillar 3 | Lifelong Learning and Exchange of Ideas | Lutz, Hartwig, Inga
Pillar 4 | Setting Guidance and Standards for the Actuarial Profession | Phillip, Lutz, Lourdes
Pillar 5 | AAE Operations and Governance | Matthias, Lutz, Hartwig

## Slide 14
ACTUARIAL ASSOCIATION OF EUROPE
Silversquare North
Boulevard Roi Albert II 4
1000 Brussels, Belgium
www.actuary.eu
Follow us on LinkedIn
and X: @InfoAAE