## Slide 1
18 June 2025
AAE Risk Management 2025
Follow up Board Meeting Paris, 18 June 2025
Inga Helmane

## Slide 2
Next steps: to be prepared for the reporting in September 2025
Risk | Name | Risk Owners (reference to AAE Board meeting: April 9, 2025)
1 | The risk of losing Member Associations’ trust, engagement and support. | Jette
2 | Risks associated with Core syllabus, CPD, Code of Conduct and MRA. | Malcolm
3 | The risk of losing attractiveness, competences and relevance as a profession. | Jette/ Phillippe
4 | The risk of lack of trust from external stakeholders. | Matthias/ Philippe
5 | The risk of a lack of volunteers. | Lourdes/ Frank/ Philippe
6 | Operational risks (key persons, cyber risks, IT issues, litigation, compliance with competition legislation, GDPR). | Matthias
7 | Financial risk | Hartwig
  Risk owners are requested to go through the mitigation actions and provide update (if necessary), liaise with CommChairs, report on an annual basis
  Steps to be taken by Risk owners:
  Assess existing / proposed (new) mitigation actions
  Liaising with relevant AAE bodies and people to communicate and promote mitigating actions
  Allocate Responsible for the mitigation actions
  Monitoring, including assessment of efficiency of mitigation actions, and reporting on risks on an annual basis
  Next Reporting date defined: AAE Board meeting September 24, 2025 (Paris, France)

## Slide 3: Appendix: Detailed insight material package
Discussed during AAE Board meeting Edinburg, 9th April 2025

## Slide 4
Agenda
Background and introduction
1
Identified risks and definitions
2
…5
…6
Risk score based on existing risk register
3
Analysis of risks with input from March 2025 Risk Survey
4
..8
..10
..17

## Slide 5
Background and Introduction
  The Board of Directors (“BoD”) has a mandate to review the overall strategy and governance of the AAE every three to five years. Risk management is an integral part of good governance for the AAE and, within the scope of this work, the BoD maintains an up-to-date risk register setting out the risks to which the AAE is exposed to, their assessment, and mitigating actions adopted in relation to each risk.
  The purpose of this document is to assist the regular review of the AAE’s risk register, including:
  Identification of risks: Reviewing the existing risk register to ensure the risks identified remain relevant. Updating the current list of risks to include additional risks, if required.
  Measurement of risks: Updating the probability and severity associated with each risk, taking into consideration any mitigation actions. To support this exercise, a survey was circulated to the BoD and AAE Committee Chairs to quantify these metrics.
  Mitigation: Reviewing the adequacy and appropriateness of existing mitigation actions and reviewing these, where required. Reviewing input from the survey in relation mitigation actions proposed in survey responses.
  Monitoring and ownership of risks: Ensuring that each risk identified is assigned to a risk owner, who will have overall responsibility for the on-going monitoring and reporting on this risk.
  Revised risk register: Providing and adopting an updated risk register, following the completion of the exercise.
  The information presented is mainly a result of the input provided by survey participants. Further discussions and analysis are required to make conclusions in relation to the risks identified and the way forward.
1
2
3
4
5

## Slide 6
Current Risk Register: Definitions & Proposed Description
Risk | Current Definition | Suggested expanded description
1 | The risk of losing Member Associations’ trust, engagement and support. | A decline in the trust or active engagement of Member Associations could undermine the AAE’s legitimacy, influence, and ability to represent the European actuarial profession effectively. This may result from perceived lack of transparency, poor communication, misalignment of strategic priorities, or ineffective delivery of value. A disengaged membership base reduces the diversity and strength of input into consultations, weakens the AAE's standing with external stakeholders, and may ultimately threaten its cohesion and sustainability.
2 | Risks associated with Core syllabus, CPD, Code of Conduct and MRA. | Inconsistencies or disputes around key professional standards — such as the Core Syllabus, Continuing Professional Development (CPD) requirements, the Code of Conduct, or the Mutual Recognition Agreement (MRAs) — could damage harmonisation efforts and mutual trust among Member Associations. Failure to maintain widely accepted, future-proof, and high-quality standards may erode the credibility of the AAE as a unifying professional body and limit actuaries' mobility across Europe, reducing the perceived value of the AAE’s work.
3 | The risk of losing attractiveness, competences and relevance as actuarial profession. | If the actuarial profession fails to stay competitive in the broader financial and data science landscape, or is perceived as lagging in emerging areas such as sustainability, AI, or broader risk management, it may lose relevance to employers, regulators, and students. This could lead to declining enrolment in actuarial education, difficulty in attracting top talent, and loss of influence in policy-making. The AAE has a key role in maintaining and promoting the reputation and evolution of the profession at European level.
4 | The risk of lack of trust from external stakeholders. | Stakeholders such as EIOPA, the European Commission, and other policy and regulatory bodies must view the AAE as a credible, neutral, and technically robust source of expertise. A loss of this trust could stem from poorly evidenced positions, slow responses to consultations, inconsistent messaging, or perceived conflicts of interest. If external confidence erodes, the AAE may lose its seat at the table in key discussions affecting the profession.
5 | The risk of a lack of volunteers. | The AAE relies heavily on volunteers from Member Associations to contribute to its workstreams, committees, consultations, and thought leadership. A shortage of engaged and suitably qualified volunteers can severely limit the AAE’s capacity to respond to EU developments, maintain professional standards, or influence the regulatory agenda. Contributing factors may include excessive time demands, unclear value proposition, or lack of recognition for volunteers’ efforts.
6 | Operational risks (key persons, cyber risks, IT issues, litigation, compliance with competition legislation, GDPR). | As a small organisation with limited operational capacity, the AAE faces risks relating to over-dependence on key individuals, inadequate IT infrastructure or cybersecurity, and potential non-compliance with legal or regulatory requirements (e.g., GDPR , competition law). Any significant disruption or breach could affect the AAE’s ability to function, lead to reputational damage, or expose it to fines and legal consequences.
7 | Financial risk | The AAE operates on a limited budget and is dependent on membership fees and potentially hard to control income sources. Unexpected increases in costs (e.g., due to inflation or changes in staffing needs), loss of members, or failure to attract new sources of funding could constrain its operations or strategic ambitions. Weak financial resilience may also limit the AAE’s ability to invest in future initiatives, recruit staff, or respond effectively to emerging needs.
  The table below outlines the existing risks included in the risk register, along with a newly identified financial risk (#7) added during recent discussions. Given that the current definitions are rather high-level, more detailed and expanded descriptions are now provided:
New

## Slide 7
Treatment of AI-Related Risk in the AAE Risk Register
  Background: Following a request from the Board, the AI-DS WG reviewed the potential inclusion of a standalone AI-related risk in the AAE Risk Register.
  Conclusion: Following discussion, it was proposed that AI-related risk does not warrant a separate entry in the register at this stage. Instead, it is more appropriately treated as a cross-sectional risk already embedded within several existing risks.
  Key AI-related concerns discussed and their alignment with existing risks:
AI-related concern | Addressed under:
Reputational risk due to improper or misunderstood use of AI (e.g., hallucinations, misuse) | Risk 6 – Operational Risks (e.g., IT and governance-related risks). Also, not a big risk for the AAE, more so for actuaries in the industry.
Risk of the AAE failing to contribute meaningfully to EU-level discussions on AI (EIOPA, EC, AI Office) | Risk 4 – Loss of trust from external stakeholders
Erosion of the profession’s relevance without AI integration | Risk 3 – Losing attractiveness, competences and relevance
Need for strong AI presence in education, learning, and professional standards | Risk 2 – Syllabus, CPD, Code of Conduct, MRA
Risk of members identifying more with external AI bodies if AAE is not active in this space | Risk 1 & 5 – Loss of Member Associations' engagement and lack of volunteers
  Existing mitigations:
  Active AI-DS Working Group,
  Responses to consultations, community building, and publications,
  Educational reform efforts through the Education Committee,
  Outreach to relevant external stakeholders on AI matters
  Additional Notes: The internal efficiency risk from AI use was assessed as minimal as AI is already employed by the AAE, e.g., for producing meeting notes.

## Slide 8
Existing Risk Scores from February 2022: Before and After Mitigation
  The table below sets out the total risk score (probability x severity) for each of the risks identified during the preparation of the previous AAE Risk Register in 2022. The scoring guide provides an indicative illustration of each risk’s potential categorization or ranking.
Risk | Name | Risk Score before Mitigation | Risk Score after Mitigation
1 | The risk of losing Member Associations’ trust, engagement and support. | 4.5 | 3.0
2 | Risks associated with Core syllabus, CPD, Code of Conduct and MRA. | 7.5 | 6.0
3 | The risk of losing attractiveness, competences and relevance as a profession. | 3.0 | 2.0
4 | The risk of lack of trust from external stakeholders. | 3.0 | 1.2
5 | The risk of a lack of volunteers. | 6.0 | 4.0
6 | Operational risks (key persons, cyber risks, IT issues, litigation, compliance with competition legislation, GDPR). | 6.0 | 6.0
7 | Financial risk | n/a | n/a
New
High | 3 | 6 | 9
Moderate | 2 | 4 | 6
Low | 1 | 2 | 3
 | Improbable | Possible | Likely
3
2
1
1
2
3
Severity
Probability
Acceptable (1-2)
Undesirable (3-4)
Unacceptable (6)
Catastrophic (9)
Scoring guide 🎯

## Slide 9
AAE Survey March 2025
  Key information requested:
  The list below sets out the information requested via the survey, issued to Directors of the Board and AAE Committee chairs.
  For each of the risks identified (1 to 7) probability and severity on a scale of 1 to 3 was requested, before and after any mitigation actions are applied.
  Participants were asked to indicate mitigation actions/solutions, including those the AAE currently applies.
  Participants:
  The table below lists the survey participants:
Name of participant | Capacity | Response (yes/no)
Frank Schiller | Board Member | Yes
Hartwig Sorger | Board Member | No
Inga Helmane | Board Member | Yes
Jette Lunding Sandqvist | Board Member | Yes
Lourdes Afonso | Board Member | Yes
Lutz Wilhelmy | Board Member | Yes
Malcolm Kemp | Board Member | Yes
Matthias Pillaudin | Board Member | Yes
Philippe Demol | Board Member | No
Birgit Kaiser | Committee Chair | Yes
Bogdan Tautan | Committee Chair | Yes
Lauri Saraste | Committee Chair | Yes
Rafael Moreno Ruiz | Committee Chair | Yes
Tatiana Bitunska | Committee Chair | Yes

## Slide 10
Risk scores based on March 2025 survey responses: Before and After Mitigation
  The table below sets out the total risk score (probability x severity) for each of the risks identified, based on the responses submitted by the survey participants in February and March 2025.
Risk | Name | Avg Risk Score before Mitigation | Avg Risk Score after Mitigation
1 | The risk of losing Member Associations’ trust, engagement and support. | 5.2 | 3.0
2 | Risks associated with Core syllabus, CPD, Code of Conduct and MRA. | 4.3 | 2.6
3 | The risk of losing attractiveness, competences and relevance as a profession. | 4.9 | 3.0
4 | The risk of lack of trust from external stakeholders. | 3.3 | 2.2
5 | The risk of a lack of volunteers. | 5.7 | 4.0
6 | Operational risks (key persons, cyber risks, IT issues, litigation, compliance with competition legislation, GDPR). | 4.3 | 2.9
7 | Financial risk | 4.2 | 2.8
High | 3 | 6 | 9
Moderate | 2 | 4 | 6
Low | 1 | 2 | 3
 | Improbable | Possible | Likely
3
2
1
1
2
3
Severity
Probability
Acceptable (1-2)
Undesirable (3-4)
Unacceptable (6)
Catastrophic (9)
Scoring guide 🎯

## Slide 11
Initial Insights February 2022 vs Survey March 2025
  The table illustrates the total risk score after mitigation (probability x severity) for each risk, providing a comparison between current scores and those implied by the responses to the March 2025 survey. For the survey calculations, the average is calculated based on the total risk score submitted by each responder:
Risk | Name | Risk Score after Mitigation 2022 Exercise | Avg Score after Mitigation Survey 2025
1 | The risk of losing Member Associations’ trust, engagement and support. | 3.0 | 3.0
2 | Risks associated with Core syllabus, CPD, Code of Conduct and MRA. | 6.0 | 2.6
3 | The risk of losing attractiveness, competences and relevance as a profession. | 2.0 | 3.0
4 | The risk of lack of trust from external stakeholders. | 1.2 | 2.2
5 | The risk of a lack of volunteers. | 4.0 | 4.0
6 | Operational risks (key persons, cyber risks, IT issues, litigation, compliance with competition legislation, GDPR). | 6.0 | 2.9
7 | Financial risk | n/a | 2.8
High | 3 | 6 | 9
Moderate | 2 | 4 | 6
Low | 1 | 2 | 3
 | Improbable | Possible | Likely
3
2
1
1
2
3
Severity
Probability
Acceptable (1-2)
Undesirable (3-4)
Unacceptable (6)
Catastrophic (9)
Scoring guide 🎯
Observations
Unchanged
Significant Reduction
Increase
Increase
Unchanged
Significant Reduction
n/a

## Slide 12
Chart: Probability
| 1.9166666666666667
Before mitigation | 2.6667
After mitigation | 2.2083
Risk #1: The risk of losing Member Associations’ trust, engagement and support
High | 3 | 6 | 9
Moderate | 2 | 4 | 6
Low | 1 | 2 | 3
 | Improbable | Possible | Likely
3
2
1
1
2
3
Severity
Probability
Acceptable (1-2)
Undesirable (3-4)
Unacceptable (6)
Catastrophic (9)
Scoring guide 🎯
Mitigating actions inspired by results:
Align AAE goals with Full Member Associations (FMAs) by understanding and addressing their evolving priorities.
Flag low delegate engagement to the respective FMAs and encourage follow-up.
Strengthen relationships through structured touchpoints, such as regular virtual meetings, updates, and feedback loops.
Ensure that AAE work is relevant and visible to FMAs — highlight outputs with practical impact and communicate clearly.
Promote knowledge sharing and mutual support among FMAs through regular exchange of information and know-how.
Enhance FMA engagement via the Presidents' Forum, field visits, and proactive communication strategies.
Respect the diversity of Member Associations by tailoring approaches and recognising national differences.
Successfully conclude Target Operating Model (TOM) discussions and maintain transparent reporting on progress.
Clarify AAE’s strategic objectives and ensure consistent communication via board liaisons and in-person exchanges.
Co-ordinate closely with other risk areas (e.g., Risk #5 on volunteers and Risk #6 on operational capacity) to manage interdependencies.
Before Mitigation
After Mitigation
3.0
5.2

## Slide 13
Chart: Probability
| 1.7916666666666667
Score Before mitigation | 2.3333
Score After mitigation | 2.0833
Risk #2: Risks associated with Core syllabus, CPD, Code of Conduct and MRA
Mitigating actions inspired by results:
Conduct regular tests and reviews of the Code of Conduct and CPD requirements to ensure their relevance and applicability across Member Associations.
Assess how the Mutual Recognition Agreement (MRA) is being applied across Europe and monitor its effectiveness, using a dedicated Task Force. Ensure the MRA remains relevant and accepted – successful reintroduction of the UK.
Support professional standards through robust governance, reinforcing professionalism as a core value of the AAE.
Provide regular updates on the Core Syllabus and develop practical tools to help smaller MAs implement changes.
Continue efforts to keep all components (Syllabus, CPD, CoPC, MRA) current and relevant in the evolving professional and regulatory environment. Identify implementation gaps in the syllabus, CPD, and CoPC across MAs and coordinate responsive actions.
High | 3 | 6 | 9
Moderate | 2 | 4 | 6
Low | 1 | 2 | 3
 | Improbable | Possible | Likely
3
2
1
1
2
3
Severity
Probability
Acceptable (1-2)
Undesirable (3-4)
Unacceptable (6)
Catastrophic (9)
Scoring guide 🎯
Before Mitigation
After Mitigation
2.6
4.3

## Slide 14
Risk #3: Losing attractiveness, competences and relevance as a profession
Chart: Probability
| 1.9583333333333333
Score Before mitigation | 2.5
Score After mitigation | 2
Expand the profession’s scope and maintain relevance by promoting actuarial expertise in non-traditional fields (e.g. sustainability, AI, risk beyond insurance).
Review and implement the AAE’s vision and mission, ensuring they are aligned with future trends.
Support flexibility and innovation while preserving the core strengths of the actuarial profession.
Strengthen the profession through education, including the development of the Core Syllabus, Competency Framework, and promotion of CPD opportunities.
Offer practical engagement opportunities, such as training, webinars, and community events to explore new topics.
Encourage sharing of experience across FMAs, especially on evolving areas like Data Science and AI.
Support Member Associations (MAs) in addressing this risk at the national level; mitigation is largely local, but the AAE can enable and facilitate.
Build on existing initiatives such as the Young Actuaries in Europe (YAI) cooperation and explore further targeted outreach.
Align this risk closely with Risk #2, ensuring consistency across professional development and relevance strategies.
Mitigating actions inspired by results:
High | 3 | 6 | 9
Moderate | 2 | 4 | 6
Low | 1 | 2 | 3
 | Improbable | Possible | Likely
3
2
1
1
2
3
Severity
Probability
Acceptable (1-2)
Undesirable (3-4)
Unacceptable (6)
Catastrophic (9)
Scoring guide 🎯
Before Mitigation
After Mitigation
3.0
4.9

## Slide 15
Risk #4: Lack of trust from external stakeholders
Mitigating actions inspired by results:
Chart: Probability
| 1.5
Score Before mitigation | 2.125
Score After mitigation | 1.8333
Maintain regular and structured engagement with key stakeholders (e.g., EIOPA, EC, AI Office), including bilateral meetings and 2–3 annual touchpoints.
Include external stakeholders in selected AAE activities, such as working groups or as speakers at events, to foster dialogue and transparency.
Ensure consistent and high-quality consultation responses, positioning the AAE as a trusted, technically robust, and constructive contributor.
Strengthen relationships with EU institutions and regulatory bodies to reinforce the AAE's role as the independent actuarial voice in Europe.
Uphold strict independence and professional ethics, including zero tolerance for improper conduct and a clear separation from industry influence.
Actively listen to stakeholder feedback, communicate openly, and always follow through on commitments.
Ensure consistency in messaging and positioning, both across AAE outputs and in direct stakeholder interactions.
High | 3 | 6 | 9
Moderate | 2 | 4 | 6
Low | 1 | 2 | 3
 | Improbable | Possible | Likely
3
2
1
1
2
3
Severity
Probability
Acceptable (1-2)
Undesirable (3-4)
Unacceptable (6)
Catastrophic (9)
Scoring guide 🎯
Before Mitigation
After Mitigation
2.2
3.3

## Slide 16
Risk #5: Lack of volunteers
Mitigating actions inspired by results:
Re-engage with FMA contacts to proactively identify new volunteers and address inactive or disengaged delegates. Collaborate with FMAs to strengthen traction and ensure sustained engagement from their members.
Recognise and celebrate volunteer contributions, for example through certificates or a “Volunteer of the Year” award.
Create an inclusive and appreciative environment where volunteers feel welcome, valued, and appreciated.
Offer meaningful internal support and engagement opportunities, including platforms where delegates can contribute to relevant and impactful topics.
Increase the visibility of volunteer work, both internally and externally, to highlight its importance and benefits.
Open up AAE priorities to FMAs and support more bottom-up initiatives that align with volunteer interests and strengths.
Communicate the benefits of volunteering clearly, such as professional exposure, skill development, and contribution to the profession.
Continue building on initiatives from the Volunteering TF, such as meet & greet sessions. ProfC deliverables on Volunteering TF.
Chart: Probability
| 2.375
Score Before mitigation | 2.4583
Score After mitigation | 2.0833
High | 3 | 6 | 9
Moderate | 2 | 4 | 6
Low | 1 | 2 | 3
 | Improbable | Possible | Likely
3
2
1
1
2
3
Severity
Probability
Acceptable (1-2)
Undesirable (3-4)
Unacceptable (6)
Catastrophic (9)
Scoring guide 🎯
Before Mitigation
After Mitigation
4.0
5.7

## Slide 17
Risk #6: Operational risks (key persons, Cyber & IT issues, legal & compliance)
Mitigating actions inspired by results:
Strengthen IT infrastructure and data management, including improved email systems, distribution lists, and a move toward more data-driven processes.
Regularly review compliance, efficiency, and process vulnerabilities, with a risk-based approach to ensure robustness.
Simplify and streamline internal processes, where possible, and outsource selectively when it adds efficiency or resilience.
Ensure access to expert advice on legal, IT, compliance, and operational matters to support sound decision-making.
Consider suggestions from TOM TF and address structural and operational risks relating to resources and key staff supporting the AAE. Use TOM TF discussions as an opportunity to strengthen the governance of the AAE and its long-term operational resilience.
Leverage AI tools to reduce administrative burden on the Secretariat.
Secure competent executive leadership (e.g., Chief Executive) to adequately oversee operational, legal, and IT risk areas.
Chart: Probability
| 1.875
Score Before mitigation | 2.25
Score After mitigation | 2.0417
High | 3 | 6 | 9
Moderate | 2 | 4 | 6
Low | 1 | 2 | 3
 | Improbable | Possible | Likely
3
2
1
1
2
3
Severity
Probability
Acceptable (1-2)
Undesirable (3-4)
Unacceptable (6)
Catastrophic (9)
Scoring guide 🎯
Before Mitigation
After Mitigation
2.9
4.3

## Slide 18
Risk #7: Financial risk
Mitigating actions inspired by results:
Ensure income and expenditure are sustainably balanced, based on considerations from TOM TF work.
Explore alternative funding sources, including potential access to EU programmes (e.g., professional development, social policy).
Adopt a conservative and prudent investment strategy, aligning with the AAE’s risk appetite and long-term financial stability goals.
Develop and maintain a clear coverage ratio policy to support sound financial planning and reserves management.
Continue pursuing a strategic, long-term financial approach, building on Hartwig’s work.
Consider financial risk in connection with Risk #1, recognising the interdependence between funding and good relationships with Member Association.
Chart: Probability
| 1.875
Score Before mitigation | 2.1667
Score After mitigation | 1.8333
High | 3 | 6 | 9
Moderate | 2 | 4 | 6
Low | 1 | 2 | 3
 | Improbable | Possible | Likely
3
2
1
1
2
3
Severity
Probability
Acceptable (1-2)
Undesirable (3-4)
Unacceptable (6)
Catastrophic (9)
Scoring guide 🎯
Before Mitigation
After Mitigation
2.8
4.2

## Slide 19
ACTUARIAL ASSOCIATION OF EUROPE
Silversquare North
Boulevard Roi Albert II 4
1000 Brussels, Belgium
www.actuary.eu
Follow us on LinkedIn
and X: @InfoAAE