## Slide 1: ECA 2026 – Board Report September 2025
ECA Steering Committee | 10/09/2025

## Slide 2: Status
General:
  The last meeting took place on 12 September 2025, the next meeting is scheduled for 17 October 2025
Recent activities:
  The sponsoring brochure was finalized, and potential partners were approached
    Confirmations:
      GOLD: Akur8, Swiss Re
      SILVER: MavenBlue, Munich Re
      BRONZE: Beltios, CERA
      National Supporters: None yet
    On-going Call for Speakers (Deadline 15 October 2025; 12 submissions received (08/09/25)
On-going tasks
  Continue sponsorship acquisition
  Promotion Call for Speakers (esp. during AAE Meetings 09/25) and discussion of plenary sessions
  Discussion of possible additional workshop offering
Sponsoring PLAN: 125.000 €
IS: 82.500 €

## Slide 3: Plenary Sessions ECA 2026 – Proposal Steering Committee
P1: EIOPA
  Welcome & Update AAE
  Keynote: Petra Hielkema (confirmed)
  Q&A with Petra
P2: ECA Partners
  Keynote: L&H Gap / Swiss Re (confirmed)
  Panel Discussion: Swiss Re, Partner 2, Partner 3
P3: ECB
  Keynote: Christine Lagarde (invited)
  Discussion with politician, e.g. Pierre Moscovici, or Insurance Europe (Frédéric de Courtois) (declined: Stéphane Séjourné (not available due to parliament week; all EU politicians will most likely not available)
P4: AI office (EU Commission) & panel tech representatives
  Keynote: Lucilla Sioli (Chair AI office, not yet invited)
  Panel: Joelle Barral (Google), Jean-Charles Samuelian (CEO ALAN), Frank Chang (IAA)
Allocation of speakers/sessions also subject to actual availability of speakers for the two days

## Slide 4
Q1 25
Q2 25
Q3 25
Q4 25
Q1 26
Q2 26
Q3 26
Steering Committee established
09/04 Business case / venue / date / congress theme agreed
15/06 First announcement sent
01/08 Call for Papers released
31/10 Speaker selected and ECA program created
01/12 Registration started
31/01 Keynote speakers announced
28/02 End of Early Bird
01/05 Plenary Sessions agreed
18/06 ECA 2026 in Paris, France
31/08 Project wrapped up
Q4 24
Host selected
Possible venues visited