## AAE Critical Action List
ID | Title | Desciption | SO | Owner | Due | Status | I/D | Involved | Done
1807-3 | PEPP | PEPP: To respond to EIOPA on the 3 requests. | 1 | MM | 2020-03-02 | 3 WGs (BS, KID, RMT) were set up | I | Philip Shier
1807-5 | USP | USP: AAE will work on this issue of potential insufficient data quality to allow the use of USP. | 1 | TOR | 2019-06-01 | TOR to update description | I
1807-7 | Consumer Protection | Consumer protection: AAE support relating to risk indicators and PRIIPS | 1 | TOR | 2019-03-01 |  | D | moved to 1905-1 | Done
1809-7 | Accountancy Europe meeting | To plan a new meeting with Accountancy Europe once the IAA paper has been made public | 1 | TOR | 2019-12-01 | delayed - AE will send an invitation - CT to follow up | I |  | done
1810-8 | Sustainability & Risk Management | To provide information how to assess the net impact of the underwriting activity of insurers regarding the sustainability; Sustainable Finance: EIOPA would like to engage with AAE focusing beyond assets so also on the liability side; To discuss sustainability in risk management with Malcolm Kemp | 2 | EK | 2019-07-01 |  | I | MKe; TOR | Done
1811-5 | Client Management System | To prepare a proposal for a client management system. If classified as non-profit organisation, chance to get licence Microsoft for free. Our collaborators, how would they be classified | 3 | LW/CT | 2020-03-03 |  | I
1901-6 | Conf calls | To research options for conference calls | 3 | MSch | 2019-04-01 | Implementation of LoopUp in progress | I |  | Done
1902-1 | Statutes | To prepare a proposal whether to change art 6 (MRA) of the Statutes | 2 | CH | 2019-04-01 | discussed in Sofia | D |  | Done
1902-2 | Review SII | To prepare a proposal how to organise the AAE approach | 1 | TOR | 2019-04-01 | discussed in Sofia | D |  | Done
1902-3 | Webinar | To prepare and organise a webinar | 3 | HW | 2019-05-01 | confirmed | I | Education Committee | Done
1902-4 | Webinar | To prepare and organise a webinar | 3 | MM | 2019-06-01 | confirmed | I | Pensions Committee/SSSC | Done
1902-6 | Webinar | To prepare and organise a webinar | 3 | Mke | 2019-12-01 | topic to be confirmed | I | Risk Management Committee | done
1902-7 | Webinar | To prepare and organise a webinar | 3 | CH | 2020-02-01 | Webinar on Professional Judgement to be presented by Siegbert. Goal is to use practical case and analysis that Siegbert did on SFCR. Date and details to be confirmed by end of November. | I | Professionalism Committee | done
1902-9 | Blog | To write a blog for the AAE website | 3 | LW | 2019-04-01 |  | I
1902-10 | Blog | To write a blog for the AAE website | 3 | TB | 2019-05-01 | ALL: to confirm preferred dates before 17 May 2019 | I
1902-11 | Blog | To write a blog for the AAE website | 3 | MKa | 2019-05-01 | ALL: to confirm preferred dates before 17 May 2019 | I
1902-12 | Blog | To write a blog for the AAE website | 3 | JMM | 2019-05-01 | ALL: to confirm preferred dates before 17 May 2019 | I
1902-13 | Blog | To write a blog for the AAE website | 3 | WS | 2019-05-01 | ALL: to confirm preferred dates before 17 May 2019 | I
1902-14 | Blog | To write a blog for the AAE website | 3 | KT | 2019-05-01 | ALL: to confirm preferred dates before 17 May 2019 | I
1902-15 | Blog | To write a blog for the AAE website | 3 | GA | 2019-05-01 | ALL: to confirm preferred dates before 17 May 2019 | I
1902-16 | Blog | To write a blog for the AAE website | 3 | MK | 2019-05-01 | ALL: to confirm preferred dates before 17 May 2019 | I
1902-17 | Blog | To write a blog for the AAE website | 3 | MM | 2019-05-01 | ALL: to confirm preferred dates before 17 May 2019 | I
1902-18 | Blog | To write a blog for the AAE website | 3 | CH | 2019-05-01 | ALL: to confirm preferred dates before 17 May 2019 | I
1902-19 | Blog | To write a blog for the AAE website | 3 | TOR | 2019-05-01 | ALL: to confirm preferred dates before 17 May 2019 | I
1902-20 | Blog | To write a blog for the AAE website | 3 | HW | 2019-05-01 | ALL: to confirm preferred dates before 17 May 2019 | I
1905-1 | EIOPA | To draft a proposal on consumer protection/PRIIPS to discuss with EIOPA | 1 | MKa | 2019-06-01 |  | D | TOR | Done
1905-2 | Legal Recognition | AAE to publish paper on Legal Recognition | 1 | CH | 2020-04-01 | Task Force Role of Actuaries to involve new Members to challenge the current Task Force work. Findings to be discussed in Bratislava. | I | Karel Goossens, Christophe Heck
1905-3 | Actuview | To start negotiations with Michael Steinmetz (DAV) | 3 | LW | 2019-06-01 | in progress | D |  | Done
1905-4 | Brussels meetings | To send personal availability in autumn to EK (updated) | 1 | ALL | 2019-06-01 | ALL: to confirm preferred dates before end of June 2019 | I
1905-5 | DG FISMA | To contact Didier Melrault (successor to Nathalie Berger) and to introduce EK | 1 | TB | 2019-06-01 |  | I |  | Done
1906-1 | Ukraine | To establish a proper contact with representatives of the Ukranian Association | 3 | MKa | 2019-07-01 | Contact established | I |  | Done
1906-3 | MRA | TF Litigation Risk Review to deliver a paper for the Spring Meetings | 3 | CH | 2020-04-01 | Task Force to receive report from IFoA to understand their current challenge and then reconvene. | I
1906-4 | Webinars | To organise a webinar in Q1 2020 re IORP stress test 2020 | 3 | MM | 2020-04-01 | FV will follow-up with MM | I
1906-5 | ECA20xx | To propose the date and venue for the next ECA | 3 | HW | 2019-07-01 |  | D |  | Done
1906-6 | Actuview | To prepare a proposal how to proceed with Actuview | 3 | LW | 2019-11-01 |  | D |  | done
1906-7 | Presidents' Meeting | To prepare a proposal for the Presidents' Meeting 2020. Falco and Cecilia to prepare draft | 3 | MKa | 2020-03-01 | To prepare draft to be disscussed in board call Feb | D | CT, FV
1907-1 | Intergenerational Fairness | To start a working group/task force | 3 | MM | 2019-08-01 | MM to update timeline | D | FV | done
1907-2 | Brussels meetings | To send personal availability to EK for the following dates: 04/09; 16/10; 14/11; 04/12 | 1 | ALL | 2019-08-01 | ALL: to confirm preferred dates before end of July 2019 | I |  | Done
Done | ECA2021 | To send a call for interest to MAs to host ECA2021 | 3 | WS | 2019-08-01 |  | D | HW | Done
1907-4 | CE position | To start contract negotiations with the preferred candidate for the CE position | 3 | EK | 2019-08-01 |  | I | FV | Done
1907-5 | AAA | To send a letter to the AAA to express our intention to continue the current relationship | 3 | EK | 2019-09-01 |  | I | TB | Done
1907-6 | AAA | To ask MAs for suggestions how to shape the relationship with AAA | 3 | EK | 2019-11-01 | Needs discussion in our next Board | D | TB | done
1908-1 | Professional judgment paper | To finalise the paper, deliver a one page summary and arrange for correct design | 3 | CH | 2020-02-19 | Reviewed by Mkam and EK. Task Force to update the documents and finalise it. | I |  | done
1908-2 | Risk Magin Paper | To finalise the paper, deliver a one page summary and arrange for correct design | 3 | MKe | 2019-09-19 | LW to review draft paper | I | LW | done
1908-3 | Committee ToR | To update the document on harmonisation of Committee ToR |  | TB | 2019-09-19 |  | D |  | Done
1908-4 | Blogs | To write a blog for the AAE website | 3 | FV | 2019-11-01 | timeline on separate Webinar schedule, FV to coordinate | I |  | done
1908-5 | Blogs | To write a blog for the AAE website | 3 | MKam | 2019-12-01 |  | I |  | Done
1908-6 | Budget 2020 | To update the Budget 2020 |  | LW | 2019-09-19 | To add/check costs allocated to SB (professional services), Actuview and the new CE | D | TB (for Actuview) | Done
1909-1 | Consultations overview | To send details of a missing EIOPA consultation | 1 | MKam | 2019-10-01 |  | I |  | done
1909-2 | GA speaker | To contact potential speakers for a presentation preceeding the GA | 3 | EK | 2019-10-01 | Invite sent to O. Karas and P. Wiedner - no response received | I |  | Done
1909-3 | Brussels meetings | To define priority contacts and to draft a message | 1 | EK | 2019-10-01 | Cecilia to arrange meetings in cooperation with EK | I | CT | done
1909-4 | Board meeting schedule 2019-2020 | To update the meeting schedule and to approve the proposed meeting dates |  | FV | 2019-10-09 |  | I |  | Done
1910-1 | MRA | To discuss concerns with IFoA and discuss in ProfC meeting on 11 October 2019 how to proceed | 2 | CH | 2019-10-01 | Meeting took place on 10 October 2019 | D |  | done
1910-2 | Consultations overview | To arrange for one pagers to summarize the consultations due on 18 October 2019 | 3 | CT | 2019-10-01 |  | I |  | done
1910-3 | ECA 2021 | To communicate decision to MAs that applied | 3 | HW | 2019-10-01 |  | I |  | Done
1910-4 | Presidents' Meeting | To liase with TB for venue Presidents Meeting in Paris on 15 May 2020 & OECD as venue? | 3 | MSch | 2020-02-01 |  | I
1910-5 | EurACI | To receive the final report from the EurACI and to discuss the next steps | 3 | FV | 2019-12-01 | To discuss in December meeting | D |  | done
EK
2001-1 | Risk register | Malcolm to update risk register (to be sent the latest version) |  |  | april | Malcolm - rr for Bratislava
2001-2 | Board structure | Formal proposal for division of work in board - operational work (vicep-chair) strategic work (chair). To be discussed at board meeting March |  | FV | 2020-03-12 | Falco and Cecilia to do proposal for board meeting Feb |  | Cecilia
2001-3 | IFoA letter | Draft IFoA AAE response to letter & propose informal meeting |  | CT | 2020-01-20 | CT to draft |  | Falco | done
2001-4 | MA Liaisons | Board members to reach out to at least one MA |  | All | 2020-02-12 | board members to contact
2001-5 | Strategy | Stakeholder and Comms strategy to be developed, paper for board April |  | CT | 2020-03-30 | to be developed |  | Falco
2001-6 | monitoring | Developing Dod's monitoring proposal for board to decide February |  | CT | 2020-02-01 | decision at Feb board meeting
2001-7 | Macedonia | Look into and contact Macedonia regarding status as observer member |  | Maria | 2020-02-01 | Maria to contact |  | Cecilia
2001-8 | Brussels visits | Fix dates for first half 2020 based on Falco's agenda & doodle |  | CT | 2020-01-01
2001-9 | EIOPA | Minutes/key action points EIOPA meeting |  | FV, EK, WS | 2020-03-01 | FV, EK, WS - draft notes ready and share with Board |  |  | done
2001-10 | Actuaries | Kristoffer Bork to write paper on role of actuariesIFRS17 |  | KB | 2020-03-01 | KB to write
2001-11 | Accountancy Europe meeting | Follow-up meeting with Accountancy Europe |  | CT | 2020-01-01 | CT to contact AE |  |  | done
2002-1 | EAN ORSA-ESAP3 | To finalise the EAN after feedback from ProfC. Board to review (LS and EK) and then present to GA for electronic approval |  | CH | 2020-04-01
2002-2 | Webinar EC | EC to organise a webinar on CPD and Ethics May/June |  | HW | 2020-04-01
2002-3 | Blogs | All to deliver blogs as outlined in the Blog overview |  | MSch | 2020-04-20
2002-4 | Bookkeeping | To liaise with SAV (Holger Walz) to draft a proposal re AAE's bookkeeping/finance |  | MSch | 2020-04-01
2003-1 | Spring Meetings Bratislava | Following cancellation of the physical meetings, to arrange virtual meetings based on the existing meeting schedule and informing all delegates |  | MSch | 2020-03-01 | Virtual meetings arranged with LoopUp |  |  | Done
2003-2 | Spring meetings | To contact Slovakia and invite them to organise Spring Meeting in future |  | CT | 2020-03-01 | Letter sent, response received: willing and contacting Croatia about SM 2021 |  | FV | Done

## Instructions
Field | Description | Format | Owner Abbr | Owner
ID | a unique identifier. Format prescribed. year month and a discrimiating number not nececarily consequtive | YYMM-NN (Text) | TB | Thomas
Title | a short description that is used while talking about the task, often starting with a gerund1, 3-5 words | text | FV | Falco
Desciption | a longer description that explains in a concise, yet self-contained manner what concern is addressed and which deliverables and milestones are intended to address it | text | AK | Ad
SO | which strategic objective is mainly supported by the action. Thus integer 1,2, or 3. We use 0 for other objectives, e.g related to operations | integer | GB | Gabor
Owner | the given name of the owner, where needed amended by a capital letter to be dicriminative | text | EK | Esko
Due | the anticipated closure date | date | TOR | Tony
Status | a medium size decription. More than just "in progress". More like "Milestone 3 achived 4 weeks ago, about 10 working day to milestone 4. on good track for delivery on time" |  | CH | Christophe
I/D | I for information and D for discussion. Discussions should happen if scope needs to be changed or deadline needs to be shifted. | "I" or "D" | KT | Kartina
Involved | List of Committees and people | text | MKam | Maria
Done | Just an internal attribute for easily selecting those tasks that are not yet done. Not for display |  | MM | Maitane
1 Those not familiar with gerund may look at https://en.wikipedia.org/wiki/Gerund

## Process
Process on the list
1) Check completeness: | are any tasks missing that the board should monitor; Inform the owner, if it's not you.
2) Weed out: | delete any of your tasks that the board should not monitor, or that is obsolete.
3) Check owner: | inform the current and proposed owner if you suggest a change of owner.
Process on each owned task
a) Revise Description (please be diligent here – this is what helps to understand what you are up to), SO allocation, due date, status, who is involved, and the done flag.
b) Decide if the item should be discussed in the February Board call and indicate accordingly.