## Sheet1
| Standards Project Team | Updated
| Work Plan 2016-2019 | 2016-09-02
| Type of Standard | Initial | Included | Informal | Report to | Informal | Exposure | Start of formal | Consultation | Publication | Decision by the | Working draft | Promulgation | 2nd exposure | Start of formal | Consultation | Publication | Decision by the | Model Standard | Model Standard | Model Standard | FMAs requested | Review date
|  | discussion | on workplan | consultation | SFPC with | consultation | draft for | consultation | period ends | of basis for | SFPC to approve | of 2nd exposure | of working draft | draft for | consultation | period ends | of basis for | SFPC to approve | submitted | promulgated | coming into | to say what they | for
|  | by SPT | as proposed | period | proposal to | period | approval | period |  | conclusions | or request a | draft to SFPC | to MAs | approval | period |  | conclusions | ESAP | to GA for | to FMAs | force | intend to do with | standard
|  |  | for development |  | develop standard | if proceeding | by SFPC |  |  |  | 2nd ED |  |  | by SFPC |  |  |  |  | approval |  |  | the standard
GCASP1 | Quality of actuarial work under Directive 2009/138/EC | 2011-05-01 | 2011-06-01 | Aug to Oct 11 | 2011-10-21 | Replaced by revised proposal for a GCASP1 on general actuarial practice modelled on ISAP1
ESAP1 | General Actuarial Practice | 2013-01-01 | 2013-04-01 |  | 2013-04-11 | Jul/Aug 2013 | 2013-09-26 | 2013-11-01 | 2014-03-01 | 2014-03-21 |  | N/A |  | N/A | N/A | N/A | N/A |  | 2014-10-03 | 2014-11-01 | 2014-12-31 | 2015-06-30
[5 empty] | Edinburgh |  | Dublin | [11 empty] | Helsinki
ESAP2 | Actuarial Function Reporting | 2011-02-01 | 2011-06-01 | Aug to Oct 11 | 2011-10-21 | 2012-09-01 | 2012-10-19 | 2012-11-01 | 2013-03-01 | 2013-05-31 | 2014-04-24 | 2014-04-24 | 2014-05-15 | 2015-05-01 | 2015-06-08 | 2015-09-04 | 2015-09-24 | 2015-09-24 | 2015-12-15 | 2016-02-03 | 2016-02-03 | 2017 | 2021
[5 empty] | Prague |  | Rome |  |  |  | Vilnius | Vilnius |  | after Paris |  |  | Bucharest | Bucharest+vote |  |  |  | Fall meeting
ESAP3 | Actuarial practice in relation to the ORSA process under S II | 2011-07-01 | 2011-10-01 | Oct 11 - Jan 14 | 2014-10-02 | Oct/Dec 2014 | 2015-09-24 | 2015-10-01 | 2016-01-31 | 2016-02-29 | 2016-03-10 | 2016-09-22 | 2016-10-10 | 2016-12-05 | 2016-12-05 | 2017-03-05 | 2017-04-28 | 2017-05-31 | 2017-05-31 | 2017-06-30 | 2017-07-01 | 2018 | 2022
[5 empty] | Helsinki |  | Bucharest |  |  |  | Nicosia | [10 empty] | Spring meeting
Possible standards for further consideration in short term
ESAP4 | The role of the AF in contributing to the RM system under S II | 2011-07-01 | 2011-08-01 | Jan - Mar 2016 | 2016-09-22
Barcelona
ESAP5 | Independent review by actuaries in the context of S II | 2013-01-01 | 2013-06-01 | Jan - Mar 2016 | 2017 | late 2017 | 2018 | 2018-04-30 | 2018-07-31 | 2018-09-15 | Following 2018 | [7 empty] | Following 2018 | 2018 | 2019-01-01 | 2019 | 2023
[5 empty] | Fall meeting |  | Spring Meeting |  |  |  | Fall meeting | [7 empty] | Fall Meeting | After Fall Meeting |  | Fall meeting
ESAP6/ ESAP1A | Governance of models (based on ISAP1A) | 2015-11-01 | 2015-11-01 | Jan - Mar 2016 |  |  | 2016-12-31 | 2016-12-31 | 2017-03-31 | 2017-05-31 | 2017 Fall meeting | [7 empty] | Following 2017 | Following 2017 | 2017-12-31 | 2018-06-30 | 2019-12-31
[7 empty] | Conditional on IAA decision(*) | [11 empty] | Fall Meeting | Fall Meeting
ESAP7 | Actuarial Function Reporting for IORPs | 2015-11-01 | 2015-11-01 | Jan - Jun 2016 | 2016-09-22
Barcelona
ESAP8 | Risk Reporting for IORPs | 2015-11-01 | 2015-11-01 | Jan - Jun 2016 | 2016-09-22
Barcelona
(*) Provided the IAA adopts ISAP1A in Cape Town; all subsequent dates depend on this assumption. If ISAP1A is exposed again by the IAA then all dates will be shifted accordingly | [17 empty] | 2017
Formulas:
Model Standard = [Decision by the]
Note on F21: Hanák, Gábor: Halt the process
Note on F30: Hanák, Gábor: Halt the process
Note on F33: Hanák, Gábor: Halt the process